## Sprint
Week #1 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 1) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10
|  |  |  | 40 | 33 | 26 | 19 | 12 | 6 | 0 | Ideal Burndown
|  |  | 40 | 40 | 31 | 28 | 12 | 6 | 3 | 0 | Remaining Hrs (Total)
Create APIs | Create Sign up API | Sandeep | 4 | 2019-05-04: 4; 2019-05-05: 3; 2019-05-06: 2; 2019-05-07: 0
| Create Login API | Sandeep | 4 | 2019-05-04: 4; 2019-05-05: 3; 2019-05-06: 2; 2019-05-07: 0
| Create Profile API | Saumil | 4 | 2019-05-04: 4; 2019-05-05: 3; 2019-05-06: 2; 2019-05-07: 0
| Create Add Card API | Sarath | 4 | 2019-05-04: 4; 2019-05-05: 3; 2019-05-06: 2; 2019-05-07: 0
| Create Order API | Sarath | 4 | 2019-05-04: 4; 2019-05-05: 3; 2019-05-06: 2; 2019-05-07: 0
| Create Payment API | Shivang | 4 | 2019-05-04: 4; 2019-05-05: 3; 2019-05-06: 2; 2019-05-07: 0
Create UI and deploy on Heroku | Design Frontend | Shivang | 4 | 4 | 4 | 4 | 2 | 1 | 0
| Desgin Frontend | Saumil | 4 | 4 | 4 | 4 | 2 | 1 | 0
| Deploy on Heroku | Saumil | 1 | 1 | 1 | 1 | 1 | 1 | 0
Dockerize APIs and deploy on AWS as EC2 instance | Create Dockerfile and create an image | Saumil | 2 | 2 | 2 | 2 | 2 | 0
| Create EC2 instance and deploy on AWS | Shivang | 2 | 2 | 2 | 2 | 2 | 0
Final Submission | Create Presentation and Final Documentation | All | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Team:
Shivang | 10 hours / Week
Saumil | 10 hours / Week
Sarath | 10 hours / Week
Sandeep | 10 hours / Week
Total Available Hours During Sprint: | 40